## Slide 1
Status on IEC 61400-4 ed.2 Design Requirements for Wind Turbine Gearboxes
US TAG for TC88 Meeting
Brian McNiff

## Slide 2: Level 5 liaison with ISO TC60
TC88 Wind energy generation systems
convenor Jens Demtröder (DK)
secretary Brian McNiff (US)
TC60 Gears
co-convenor Dr. Thomas Tobie (DE)

## Slide 3: Project Scope
Standard is focused on design requirements
Informative text and annexes were calved off to minimize some conflicting items (e.g., simple design life for bearings )
Standard is split into following documents
  IEC 61400-4 ed.2 Design requirements for windturbine gearboxes
  IEC/TS 61400-4-1 Reliability assessment of drivetrain components in windturbines
  IEC/TR 61400-4-2 Lubrication of drivetrain components in windturbines
  IEC/TR 61400-4-3 Explanatory notes on IEC 61400-4 - Supportive information for windturbine gearbox design

## Slide 4: Status/ Ed2 Modifications
Focus on modifications and updates:
  Reliability new TS, from AGMA 6006
  Plain bearings brand new
  Structures shifted to 61400-8
  Verification risk based approach
  Gears, rolling bearings slight modifications
  Lubrication modified + new TR
expert task group drafts completed into WD Feb 2020
now resolving 1000+ comments to Working Draft hopeful that this will reduce comments to CD
Expect completion Apr 2021
Upcoming meetings 12-13-14 before end of 2021

## Slide 5: Status/Timeline
IEC 61400-4 ed.2 is in preparatory stage, WD2?
  Decide after WD1 comment resolution whether WD2 or CD
Intend to publish TS and TR at same time as Ed2
  Will soon circulate TS-4-1, TR-4-2, TR-4-3 for WD Comment
  CD soon after - they are non-normative not expecting mucho comments
 | Start date | WD | CD | CDV | IS
Current approved | Oct. ‘17 |  | Jan ’20 | Sept. ’20 | Dec. ’21
Current achieved or estimate |  |  |  |  | 
IEC 61400-4 ed.2 | Oct. ‘17 | Feb ’20 | June. ’21 (WD2?) |  | 
reliability TS-1 | June ’18 | Mar ’21 | Dec. ’21 |  | 
lubrication TR-2 | June ’18 | Mar ’21 | Dec ’21 |  | 
explanatory notes TR-3 | June ‘18 | Mar ’21 | Dec ’21 |  | 
I hope that TAG will be
asked to comment on
these documents before
end of 2021